## Week7
MCI Project Weekly Time Sheet
Team-17E |  | Student ID: | a1881583 |  |  |  | Week starting: Week7
Day | Date | Time In | Time Out | Total hours | keyword | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2024-04-22 | 38:00 | 40:00 | 2 | Homepage Completion | Finalize the homepage design | Essential for user engagement and initial user interaction | Completed initial homepage design
Tuesday | 2024-04-23 | 47:00 | 41:00 | 6 | Self-learning | Learn Tailwind CSS | Enhances styling capabilities for responsive design | Applied Tailwind CSS to homepage components
Wednesday | 2024-04-24 | 34:00 | 42:00 | 8 | Homepage Completion | Initial Implementation of homepage functionality(top menu, hero, how it works, recommended catrgories, testmonials, trusted by footer sections etc., ) | Ensures interactive and functional homepage | Integrated interactive elements
Thursday | 2024-04-25 | 35:00 | 39:00 | 4 | Homepage Completion | Complete, Review and refine homepage | Ensures high quality and usability | Refined homepage based on initial feedback
Friday | 2024-04-26 | 47:00 | 40:00 | 5 | Client meeting + first mile stone check | Showcase current build to the client and discuss feedback | Gathers essential input for iterative improvements | Tethered client feedback for further development
|  |  | Total | 25

## Week8
MCI Project Weekly Time Sheet
Team-17E |  | Student ID: | a1881583
Day | Date | Time In | Time Out | Total hours | Keyword | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 29/4 | 35:00 | 3:00 PM | 4 | Self-learning | Learn Redux | Enhances state management capabilities | Applied Redux for state management
Tuesday | 30/4 | 47:00 | 3:00 PM | 4 | Joblist Page Completion | Finalize joblist page design | Ensures a comprehensive and user-friendly job browsing experience | Completed joblist page design
Wednesday | 1/5 | 34:00 | 6:00 PM | 8 | Joblist Page Completion | Implement joblist page functionality | Essential for displaying job listings interactively | Integrated interactive job listing features
Thursday | 2/5 | 35:00 | 5:00 PM | 6 | Joblist Page Completion | Review and refine joblist page | Ensures high quality and usability | Refined joblist page based on initial feedback
Friday | 3/5 | 39:00 | 6:00 PM | 3 | Team Meeting (Second milestone preparation) | Discuss progress and next stepson the second milestone | Keeps team aligned and identifies any issues to be addressed | Plan for next week's tasks and address concerns
|  |  | Total | 25

## Week9
MCI Project Weekly Time Sheet
Team-17E |  | Student ID: | a1881583
Day | Date | Time In | Time Out | Total hours | Keyword | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 6/5 | 35:00 | 5:00 PM | 6 | Freelancer Profile Page | Design freelancer profile page | Provides a comprehensive view of freelancer skills and portfolio | Completed freelancer profile page design
Tuesday | 7/5 | 47:00 | 4:00 PM | 5 | Freelancer Profile Page | Implement freelancer profile page functionality | Essential for freelancers to showcase their work | Integrated interactive freelancer profile features
Wednesday | 8/5 | 34:00 | 5:00 PM | 7 | Employer Profile Page | Design employer profile page | Allows employers to display company details and job offerings | Completed employer profile page design
Thursday | 9/5 | 35:00 | 4:00 PM | 5 | Employer Profile Page | Implement employer profile page functionality | Essential for employers to manage their profiles and postings | Integrated interactive employer profile features
Friday | 10/5 | 37:00 | 3:00 PM | 2 | Team Meeting | Check implementation of second milestone and make testing plan | Ensures milestone completion and prepares for thorough testing | Finalized testing plan based on milestone review
|  |  | Total | 25

## Week10
MCI Project Weekly Time Sheet
Team-17E |  | Student ID: | a1881583
Day | Date | Time In | Time Out | Total hours | Keyword | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 13/5 | 34:00 | 4:00 PM | 5 | Self-learning | Study Node.js | Enhances backend development skills | Applied Node.js knowledge to backend improvements
Tuesday | 14/5 | 47:00 | 5:00 PM | 6 | Collaboration | Collaborate on iterating through all pages, frontend and backend | Ensures consistency and functionality across the platform | Refined and improved page functionalities
Wednesday | 15/5 | 24:00 | 6:00 PM | 6 | Collaboration | Collaborate on iterating through all pages, frontend and backend | Ensures consistency and functionality across the platform | Refined and improved page functionalities
Thursday | 16/5 | 1:00 PM | 5:00 PM | 4 | Collaboration | Collaborate on iterating through all pages, frontend and backend | Ensures consistency and functionality across the platform | Refined and improved page functionalities
Friday | 17/5 | 37:00 | 5:00 PM | 4 | Team Meeting | Check second milestone implementation and review testing plan | Ensures all second milestone tasks are completed and testing is thorough | Finalized second milestone, prepared for testing
|  |  | Total | 25

## Week11
MCI Project Weekly Time Sheet
Team-17E |  | Student ID: | a1881583
Day | Date | Time In | Time Out | Total hours | Keyword | Task | How does it fit to project plan? | Outcome/Next action
Monday | 20/5 | 35:00 | 4:00 PM | 5 | Automated Testing (round1) | Conduct automated tests on the platform | Ensures platform stability and reliability | Identify and document issues, ensure automated tests pass
Tuesday | 21/5 | 47:00 | 4:00 PM | 5 | Self-testing (round1) | Perform manual testing on the platform | Validates user experience and functionality | Document issues, ensure all manual tests pass
Wednesday | 22/5 | 34:00 | 3:00 PM | 5 | User Testing (round1) | Conduct user testing with real users | Gathers real-world feedback and usability insights | Collect user feedback, identify areas for improvement
Thursday | 23/5 | 35:00 | 4:00 PM | 5 | Functionality Improvement | Refine functionality and improve UI/UX based on testing feedback | Enhances user experience and platform functionality | Implement improvements, resolve identified issues
Friday | 24/5 | 37:00 | 6:00 PM | 5 | Team Meeting | Review testing results and finalize improvements | Ensures all feedback and issues are addressed | Finalize platform for final review
|  |  | Total | 25

## Week12
MCI Project Weekly Time Sheet
Team-17E |  | Student ID: | a1881583
Day | Date | Time In | Time Out | Total hours | Keyword | Task | How does it fit to project plan? | Outcome/Next action
Monday | 27/5 | 35:00 | 4:00 PM | 5 | Automated Testing (round2) | Conduct automated tests on the platform | Ensures platform stability and reliability | Identify and document issues, ensure automated tests pass
Tuesday | 28/5 | 47:00 | 5:00 PM | 6 | Self-testing (round2) | Perform manual testing on the platform | Validates user experience and functionality | Document issues, ensure all manual tests pass
Wednesday | 29/5 | 37:00 | 6:00 PM | 5 | User Testing (round2) | Conduct user testing with real users | Gathers real-world feedback and usability insights | Collect user feedback, identify areas for improvement
Thursday | 30/5 | 35:00 | 6:00 PM | 7 | Functionality Improvement | Refine functionality and improve UI/UX based on testing feedback | Enhances user experience and platform functionality | Implement improvements, resolve identified issues
Friday | 31/5 | 40:00 | 6:00 PM | 2 | Client Meeting | Showcase the complete software to the client, discuss feedback | Ensures all project goals and client requirements are met | Gather final client feedback, prepare for project delivery
|  |  | Total | 25